## Product Backlog
ID | User Story | Priority | Est. Story Points | Acceptance Criteria
PB-001 | As an applicant, I want to enter my personal & financial details so that I can check loan eligibility | High | 8 | All mandatory fields available, validations in place, correct mapping to model features
PB-002 | As a data scientist, I want cleaned historical loan data so I can train accurate models | High | 13 | Missing values handled, categorical encoded, logs applied where needed
PB-003 | As a developer, I want a preprocessing function to convert inputs to model features | High | 5 | Preprocess returns feature vector matching model order
PB-004 | As a user, I want a Streamlit UI to submit my details and get a prediction | High | 8 | UI fields map to model inputs and displays result
PB-005 | As a user, I want a conversational chatbot to collect inputs step-by-step | Medium | 8 | Chat collects same fields as UI with validation and shows summary
PB-006 | As a devops engineer, I want the model packaged (model.pkl) and loaded reliably | High | 3 | Model loads without error and predictions consistent
PB-007 | As a tester, I want unit tests for preprocessing and prediction functions | High | 5 | Unit tests cover edge cases and pass in CI
PB-008 | As a product owner, I want authentication for protected pages | Medium | 3 | Login uses demo creds and restricts access to form/chatbot
PB-009 | As a user, I want clear error messages and guidance when inputs are invalid | Medium | 3 | Validations exist and messages are user-friendly
PB-010 | As a team, we want deployment scripts to run the Flask app and Streamlit app | Medium | 8 | Deployment documented and apps runnable on server

## Sprint Backlog
Sprint | Tasks | Owner | Est. Hrs | Status
Sprint 1 | Data collection, EDA, basic cleaning, create preprocessing pipeline | Data Scientist | 40 | Planned
Sprint 1 | Train baseline models (Logistic Regression, Decision Tree), measure metrics | Data Scientist | 32 | Planned
Sprint 1 | Create REST API endpoint /predict using Flask | Backend Dev | 24 | Planned
Sprint 2 | Develop Streamlit UI and integrate model.pkl | Frontend Dev | 30 | Planned
Sprint 2 | Implement chatbot flow in Streamlit with validations | Frontend Dev | 28 | Planned
Sprint 2 | Write unit tests and basic integration tests | QA | 24 | Planned
Sprint 3 | Fix defects, harden input validation, add authentication | All | 40 | Planned
Sprint 3 | Prepare deployment scripts and documentation | DevOps | 32 | Planned

## Stand up Meeting
Date | Team Member | Yesterday | Today | Blockers
2025-11-17 | Alice (Data Scientist) | Data cleaning & baseline model | Hyperparameter tuning for Random Forest | Missing certain fields in dataset
2025-11-17 | Bob (Backend Dev) | Flask predict endpoint scaffolded | Integrate model.pkl and secure endpoint | Model file path issues on server
2025-11-17 | Chetan (Frontend) | Streamlit layout for prediction page | Add sliders and image assets | Image file loan.png missing in container path

## Retrospection
Sprint | What went well | What didn't go well | Action Items
Sprint 1 | Completed data cleaning and baseline models | Underestimated time for data imputation | Add data audit task to future sprints; allocate buffer
Sprint 2 | Streamlit UI prototype created | Chatbot validation edge cases missed | Add more validation tests; pair-program chatbot logic
Sprint 3 | Auth and session management implemented (demo creds) | Deployment automation not started | Schedule DevOps sprint for deployment scripts