## Defects
Defect ID | Module | Title | Description | Severity | Priority | Reported By | Assigned To | Reported Date | Status | Root Cause | Resolution
D001 | Preprocessing | Credit score mapping incorrect | Condition checks use 850 threshold inconsistently across files (800 vs 850). Results in false negatives/positives | High | P1 | QA | Alice | 2025-11-17 | Open | Inconsistent threshold in code variants (chatbot/streamlit/flask) | Standardize to 800 or 850 after PO decision
D002 | Chatbot | Chatbot hangs on initial prompt | Chatbot sometimes doesn't progress from 'Are you ready?' to first question when user types 'Yes' with capitalization variations | Medium | P2 | QA | Chetan | 2025-11-17 | Fixed | Case-sensitive comparison in some branches | Normalize input to lower() in all checks
D003 | Model Loading | Model file path error on server | Flask app fails to load model.pkl when run from different working directory | High | P1 | DevOps | Bob | 2025-11-17 | Fixed | Relative path usage instead of __file__-based path | Use os.path.join(os.path.dirname(__file__), 'model.pkl')
D004 | Streamlit UI | Loan term slider misleading units | Loan term labeled as days in some places and months in others; users confused | Low | P3 | UX | Chetan | 2025-11-17 | Open | Inconsistent label text | Standardize to days and update helper text

## Summary
Summary | Value
Total Defects | 4
Open | 2
Fixed | 2